## Summary_20201015_v3.1
# | Task Name | Duration | Start | Finish | Predecessors | PaymentMilestone
1 | CIS Revamp- Revised Plan 20201015_V3.1 | 1839 days | Mon 17/07/10 | Thu 25/01/23
2 | Project Planning | 86 days | Mon 17/07/10 | Mon 17/11/06 |  | Y
3 | Due Diligence Exercise and Report | 79 days | Thu 17/08/10 | Tue 17/11/28 |  | Y
4 | Project Design & Documentation | 330 days | Mon 17/12/04 | Fri 19/03/08 |  | Y
5 | Release 1 - Initial Development | 173 days | Fri 19/03/15 | Tue 19/11/12
6 | Web portal | 82 days | Fri 19/03/15 | Sun 19/07/07 |  | Y
7 | User Access Management | 82 days | Fri 19/03/15 | Sun 19/07/07 |  | Y
8 | Information Provisioning | 173 days | Fri 19/03/15 | Tue 19/11/12
9 | Release 1 Closure | 380 days | Wed 19/11/13 | Mon 21/07/05
10 | Deployment & internal testing before rerelease for client testing | 23 days | Wed 19/11/13 | Fri 19/12/13
11 | Release 1 retest (Module 3)- client environment | 2 days | Thu 20/01/09 | Fri 20/01/10 | 10
12 | Release 1 UAT (Module 3) | 2 days | Thu 20/01/16 | Fri 20/01/17 | 11
13 | Release 1- Module 3 Signoff (Create & sign documentation pack) | 5 days | Mon 20/01/20 | Fri 20/01/24 | 12
14 | Classify & Workshop UAT Feedback | 1 day | Mon 20/01/27 | Mon 20/01/27 | 13
15 | Module 3 Traceability Resolution | 319 days | Tue 20/02/18 | Tue 21/06/29 | 14
16 | Initial Workshopping | 14 days | Tue 20/02/18 | Fri 20/03/06
17 | Requirements Detailing | 42 days | Mon 20/03/09 | Mon 20/05/11
18 | Development & Testing | 254 days | Tue 20/05/12 | Tue 21/06/15
19 | Development & Unit Testing | 220 days | Tue 20/05/12 | Wed 21/04/28 | 28
20 | Current System- Analysis of FRS addendums | 39 days | Tue 20/05/12 | Mon 20/07/06 | 28
21 | Current System- Database, Existing Application flow | 72 days | Mon 20/06/01 | Thu 20/09/10
22 | Architecture of revised System- Architecture changes - based on FRS addendums | 112 days | Mon 20/06/01 | Fri 20/11/06
23 | Deployment in DW server- Iterative - monthly deployments for review | 100 days | Wed 20/09/30 | Wed 21/03/24
24 | Review/ Testing- Internal - DW Testing (Monthly Releases) | 122 days | Wed 20/09/30 | Wed 21/04/28
25 | Work Package 1- Wireframes, Workflow Studio | 71 days | Tue 20/07/21 | Thu 20/10/29
26 | Work Package 2- GIS- No Integration | 30 days | Thu 20/10/01 | Wed 20/11/11
27 | Work Package 3- UAM, Workflow Studio, Web Portal | 42 days | Thu 20/10/01 | Fri 20/11/27
28 | Work Package 4- GIS- No Integration | 16 days | Fri 20/11/13 | Tue 20/12/15
29 | Work Package 5- UAM & IM | 25 days | Mon 20/11/02 | Tue 20/12/22
30 | Work Package 6- GIS- No Integration | 8 days | Fri 20/12/18 | Wed 21/01/20
31 | Work Package 7- UAM & IM | 14 days | Tue 20/12/22 | Thu 21/01/28
32 | Work Package 8- IM | 20 days | Fri 21/01/29 | Thu 21/02/25
33 | Work Package 9- GIS- With Integration | 35 days | Fri 21/01/22 | Thu 21/03/11
34 | Work Package 10- Dashboards, Back End services | 20 days | Fri 21/02/26 | Fri 21/03/26
35 | Work Package 11- Updated Knowledge Base | 20 days | Tue 21/03/16 | Thu 21/04/15
36 | Review Session 1- Wireframes, Workflow Studio- DW Environment | 1 day | Fri 20/10/30 | Fri 20/10/30 | 36
37 | Review Session 2- GIS- No Integration- DW Environment | 1 day | Thu 20/11/12 | Thu 20/11/12 | 51
38 | Review Session 3- UAM, Workflow Studio- DW Environment | 1 day | Mon 20/11/30 | Mon 20/11/30 | 58
39 | Review Session 4- GIS- No Integration- DW Environment | 0 days | Thu 20/12/17 | Thu 20/12/17 | 87
40 | Review Session 5- UAM & IM- DW Environment | 0 days | Wed 20/12/23 | Wed 20/12/23 | 92
41 | Review Session 6- GIS- No Integration- DW Environment | 1 day | Thu 21/01/21 | Thu 21/01/21 | 125
42 | Review Session 7- UAM & IM- DW Environment | 1 day | Fri 21/01/29 | Fri 21/01/29 | 130
43 | Review Session 8- IM- DW Environment | 1 day | Fri 21/02/26 | Fri 21/02/26 | 163
44 | Review Session 9- GIS- With Integration- DW Environment | 1 day | Thu 21/03/11 | Thu 21/03/11 | 175
45 | Review Session 10- Dashboards, Back End services- DW Environment | 1 day | Mon 21/03/29 | Mon 21/03/29 | 187
46 | Review Session 11- Updated Knowledge Base- DW Environment | 1 day | Thu 21/04/15 | Thu 21/04/15 | 196
47 | Revision of test cases | 2 days | Thu 21/04/29 | Fri 21/04/30 | 30
48 | Testing- Data World | 5 days | Mon 21/05/03 | Fri 21/05/07 | 378
49 | Test report- Data World | 4 days | Mon 21/05/10 | Thu 21/05/13 | 379
50 | Submission of test report to client | 1 day | Fri 21/05/14 | Fri 21/05/14 | 380
51 | Client review of test report | 2 days | Mon 21/05/17 | Tue 21/05/18 | 381
52 | Demonstration to client- DW environment | 1 day | Wed 21/05/19 | Wed 21/05/19 | 382
53 | Further client feedback incorporated | 5 days | Thu 21/05/20 | Wed 21/05/26 | 383
54 | Update of existing user manuals/ helpfiles / material | 4 days | Thu 21/05/27 | Tue 21/06/01 | 384
55 | Rollout to Client Test environment | 2 days | Wed 21/06/02 | Thu 21/06/03 | 385
56 | DW- client environment testing | 2 days | Fri 21/06/04 | Mon 21/06/07 | 386
57 | Test report creation | 2 days | Tue 21/06/08 | Wed 21/06/09 | 387
58 | Submission of test report to client | 1 day | Thu 21/06/10 | Thu 21/06/10 | 388
59 | Client review of test report | 3 days | Fri 21/06/11 | Tue 21/06/15 | 389
60 | UAT- End to End, including changes to previous system functionality as per addendums | 3 days | Thu 21/06/17 | Mon 21/06/21 | 390
61 | Creation of revised delivery pack | 3 days | Tue 21/06/22 | Thu 21/06/24 | 391
62 | Review & Signoff - revised delivery pack | 3 days | Fri 21/06/25 | Tue 21/06/29 | 392 | Y
63 | Production Rollout- Release 1 | 3 days | Wed 21/06/30 | Fri 21/07/02 | 393
64 | PSC Approval- Go Ahead to proceed with Release 2 | 1 day | Mon 21/07/05 | Mon 21/07/05 | 394
65 | Release 2 - Release of Purchase Order | 651 days | Wed 19/11/13 | Mon 22/09/05
66 | BRS Phase | 18 days | Wed 19/11/13 | Fri 19/12/06
67 | FRS phase | 60 days | Tue 21/07/06 | Wed 21/09/29 | 395
68 | Preparation for FRS Sessions | 5 days | Tue 21/07/06 | Mon 21/07/12
69 | Sessions with Deeds PTA/ SG PTA | 4 days | Tue 21/07/13 | Fri 21/07/16 | 402
70 | FRS Sessions | 5 days | Mon 21/07/19 | Fri 21/07/23 | 403
71 | Module 5 (Lodgement) | 26 days | Mon 21/07/26 | Tue 21/08/31
72 | Module 6 (Examinations) | 24 days | Wed 21/08/11 | Mon 21/09/13
73 | Module 4 (Reservations) | 25 days | Wed 21/08/25 | Wed 21/09/29
74 | Development Phase, Testing Phase | 231 days | Wed 21/09/01 | Mon 22/09/05
75 | Module 5 (Lodgement) | 98 days | Wed 21/09/01 | Mon 22/02/21 |  | Y
76 | Module 6 (Examinations) | 73 days | Tue 22/02/22 | Thu 22/06/09 |  | Y
77 | Module 4 (Reservations) | 49 days | Fri 22/06/10 | Fri 22/08/19 |  | Y
78 | Release 2 Signoff | 5 days | Mon 22/08/22 | Fri 22/08/26 | 453
79 | Production Rollout- Release 2 | 5 days | Mon 22/08/29 | Fri 22/09/02 | 454
80 | PSC Approval- Go Ahead to proceed with Release 3 | 1 day | Mon 22/09/05 | Mon 22/09/05 | 455
81 | Release 3- Release of Purchase Order | 292 days | Tue 22/09/06 | Tue 23/11/21
82 | BRS Phase | 47 days | Tue 22/09/06 | Wed 22/11/09
83 | Module 7 (Archive) | 23 days | Tue 22/09/06 | Thu 22/10/06
84 | Module 8 (Maintenance) | 23 days | Fri 22/09/16 | Tue 22/10/18
85 | Module 9 (Reports) | 23 days | Wed 22/09/28 | Fri 22/10/28
86 | Module 10 (Common Tools) | 23 days | Mon 22/10/10 | Wed 22/11/09
87 | FRS Phase | 52 days | Thu 22/11/10 | Tue 23/02/14
88 | Preparation for FRS Sessions | 2 days | Thu 22/11/10 | Fri 22/11/11 | 486
89 | FRS Sessions | 7 days | Mon 22/11/14 | Tue 22/11/22 | 488
90 | Module 7 (Archive) | 23 days | Wed 22/11/23 | Tue 23/01/17
91 | Module 8 (Maintenance) | 23 days | Wed 22/12/07 | Tue 23/01/31
92 | Module 9 (Reports) | 18 days | Fri 23/01/13 | Tue 23/02/07
93 | Module 10 (Common Tools) | 18 days | Fri 23/01/20 | Tue 23/02/14
94 | Development Phase, Testing Phase | 213 days | Wed 23/01/18 | Tue 23/11/21
95 | Module 7 (Archive) | 53 days | Wed 23/01/18 | Mon 23/04/03 |  | Y
96 | Module 8 (Maintenance) | 90 days | Tue 23/04/04 | Tue 23/08/15 |  | Y
97 | Module 9 (Reports) | 32 days | Wed 23/08/16 | Thu 23/09/28 |  | Y
98 | Module 10 (Common Tools) | 28 days | Fri 23/09/29 | Tue 23/11/07 |  | Y
99 | Release 3 Signoff | 5 days | Wed 23/11/08 | Tue 23/11/14 | 554
100 | Production Rollout- Release 3 | 5 days | Wed 23/11/15 | Tue 23/11/21 | 555
101 | Project Closure | 44 days | Wed 23/11/22 | Mon 24/02/12 | 556 | Y
102 | Post Go-Live Support | 240 days | Tue 24/02/13 | Thu 25/01/23 | 557 | Y

## Detailed_20201015_v3.1
# | Task Name | Duration | Start (YYMMDD) | Finish (YYMMDD) | Predecessors
1 | CIS Revamp- Revised Plan 20201015_V3.1 | 1839 days | Mon 17/07/10 | Thu 25/01/23
2 | Project Planning | 86 days | Mon 17/07/10 | Mon 17/11/06
3 | Due Diligence Exercise and Report | 79 days | Thu 17/08/10 | Tue 17/11/28
4 | Project Design & Documentation | 330 days | Mon 17/12/04 | Fri 19/03/08
5 | Release 1 - Initial Development | 173 days | Fri 19/03/15 | Tue 19/11/12
6 | Web portal | 82 days | Fri 19/03/15 | Sun 19/07/07
7 | User Access Management | 82 days | Fri 19/03/15 | Sun 19/07/07
8 | Information Provisioning | 173 days | Fri 19/03/15 | Tue 19/11/12
9 | Release 1 Closure | 380 days | Wed 19/11/13 | Mon 21/07/05
10 | Deployment & internal testing before rerelease for client testing | 23 days | Wed 19/11/13 | Fri 19/12/13
11 | Release 1 retest (Module 3)- client environment | 2 days | Thu 20/01/09 | Fri 20/01/10 | 10
12 | Release 1 UAT (Module 3) | 2 days | Thu 20/01/16 | Fri 20/01/17 | 11
13 | Release 1- Module 3 Signoff (Create & sign documentation pack) | 5 days | Mon 20/01/20 | Fri 20/01/24 | 12
14 | Classify & Workshop UAT Feedback | 1 day | Mon 20/01/27 | Mon 20/01/27 | 13
15 | Module 3 Traceability Resolution | 319 days | Tue 20/02/18 | Tue 21/06/29 | 14
16 | Initial Workshopping | 14 days | Tue 20/02/18 | Fri 20/03/06
17 | Workshop with DRDLR- Module 3 Traceability | 1 day | Tue 20/02/18 | Tue 20/02/18
18 | Review and update plan | 3 days | Wed 20/02/19 | Fri 20/02/21 | 17
19 | Generate CR - submit to project team | 2 days | Mon 20/02/24 | Tue 20/02/25 | 18
20 | PSC- present revised plan | 1 day | Wed 20/02/26 | Wed 20/02/26 | 19
21 | Approval for revised plan granted (time includes prep for sessions) | 7 days | Thu 20/02/27 | Fri 20/03/06 | 20
22 | Requirements Detailing | 42 days | Mon 20/03/09 | Mon 20/05/11
23 | Client Workshops- detail requirements | 5 days | Mon 20/03/09 | Fri 20/03/13 | 21
24 | Documentation of requirements, submit for review | 10 days | Mon 20/03/16 | Fri 20/03/27 | 23
25 | Client review of revised requirements | 5 days | Mon 20/03/30 | Fri 20/04/03 | 24
26 | Incorporation of amendments, Submission to Project Sponsor | 12 days | Mon 20/04/06 | Thu 20/04/23 | 25
27 | Submission of revised addendums to client team | 1 day | Fri 20/04/24 | Fri 20/04/24 | 26
28 | Final client review and approval of requirements (VC Workshops) | 9 days | Tue 20/04/28 | Mon 20/05/11 | 27
29 | Development & Testing | 254 days | Tue 20/05/12 | Tue 21/06/15
30 | Development & Unit Testing | 220 days | Tue 20/05/12 | Wed 21/04/28 | 28
31 | Current System- Analysis of FRS addendums | 39 days | Tue 20/05/12 | Mon 20/07/06 | 28
32 | Current System- Database, Existing Application flow | 72 days | Mon 20/06/01 | Thu 20/09/10
33 | Architecture of revised System- Architecture changes - based on FRS addendums | 112 days | Mon 20/06/01 | Fri 20/11/06
34 | Deployment in DW server- Iterative - monthly deployments for review | 100 days | Wed 20/09/30 | Wed 21/03/24
35 | Review/ Testing- Internal - DW Testing (Monthly Releases) | 122 days | Wed 20/09/30 | Wed 21/04/28
36 | Work Package 1- Wireframes, Workflow Studio | 71 days | Tue 20/07/21 | Thu 20/10/29
37 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Theme\Master Layout | 71 days | Tue 20/07/21 | Thu 20/10/29
38 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Application HTML Flow | 71 days | Tue 20/07/21 | Thu 20/10/29
39 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Registration Page | 71 days | Tue 20/07/21 | Thu 20/10/29
40 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Sign in | 71 days | Tue 20/07/21 | Thu 20/10/29
41 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- After login- Home Page | 71 days | Tue 20/07/21 | Thu 20/10/29
42 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- All the modules wireframe | 71 days | Tue 20/07/21 | Thu 20/10/29
43 | Internal User Application- Workflow (Common Features)- Workflow Studio- Create new process flow - National | 71 days | Tue 20/07/21 | Thu 20/10/29
44 | Internal User Application- Workflow (Common Features)- Workflow Studio- Define all the configuration | 71 days | Tue 20/07/21 | Thu 20/10/29
45 | Internal User Application- Workflow (Common Features)- Workflow Studio- Publish process for all Provinces | 71 days | Tue 20/07/21 | Thu 20/10/29
46 | Internal User Application- Workflow (Common Features)- Workflow Studio- Province will have feature to customize the process flow | 71 days | Tue 20/07/21 | Thu 20/10/29
47 | Internal User Application- Workflow (Common Features)- Workflow Studio- Configuration Turnaround Time | 71 days | Tue 20/07/21 | Thu 20/10/29
48 | Internal User Application- Workflow (Common Features)- Workflow Studio- Configure Request prefix and Suffix | 71 days | Tue 20/07/21 | Thu 20/10/29
49 | Internal User Application- Workflow (Common Features)- Workflow Studio- Tracking number configuration for all type of request | 71 days | Tue 20/07/21 | Thu 20/10/29
50 | Internal User Application- Administrative modules- List management- List Management of system | 71 days | Tue 20/07/21 | Thu 20/10/29
51 | Work Package 2- GIS- No Integration | 30 days | Thu 20/10/01 | Wed 20/11/11
52 | GIS- Spatial Viewer- Measure Tool | 30 days | Thu 20/10/01 | Wed 20/11/11
53 | GIS- Spatial Viewer- Layer Manager | 30 days | Thu 20/10/01 | Wed 20/11/11
54 | GIS- Spatial Viewer- Map Legend | 30 days | Thu 20/10/01 | Wed 20/11/11
55 | GIS- Spatial Viewer- Identify Tool | 30 days | Thu 20/10/01 | Wed 20/11/11
56 | GIS- Spatial Viewer- Map Navigation Tools | 30 days | Thu 20/10/01 | Wed 20/11/11
57 | GIS- Spatial Viewer- Parametrised Viewer | 30 days | Thu 20/10/01 | Wed 20/11/11
58 | Work Package 3- UAM, Workflow Studio, Web Portal | 42 days | Thu 20/10/01 | Fri 20/11/27
59 | External User Application - User Access Management- External User Management- Registration (PLS, Architect , Assistance, Conveyancer and all other) | 42 days | Thu 20/10/01 | Fri 20/11/27
60 | External User Application - User Access Management- External User Management- Verify Professional Registration | 42 days | Thu 20/10/01 | Fri 20/11/27
61 | External User Application - User Access Management- External User Management- Sign in | 42 days | Thu 20/10/01 | Fri 20/11/27
62 | External User Application - User Access Management- External User Management- Deactivate account as per role in hierarchy | 42 days | Thu 20/10/01 | Fri 20/11/27
63 | External User Application - User Access Management- External User Management- Reactivate account | 42 days | Thu 20/10/01 | Fri 20/11/27
64 | External User Application - User Access Management- External User Management- PLS mange assistants | 42 days | Thu 20/10/01 | Fri 20/11/27
65 | External User Application - User Access Management- External User Management- Forget Password | 42 days | Thu 20/10/01 | Fri 20/11/27
66 | External User Application - User Access Management- External User Management- Reset Password | 42 days | Thu 20/10/01 | Fri 20/11/27
67 | External User Application - User Access Management- External User Management- User Profile | 42 days | Thu 20/10/01 | Fri 20/11/27
68 | External User Application - Common Feature- other features- Home Page | 42 days | Thu 20/10/01 | Fri 20/11/27
69 | External User Application - Common Feature- other features- Notification Section | 42 days | Thu 20/10/01 | Fri 20/11/27
70 | External User Application - Common Feature- other features- Inbox | 42 days | Thu 20/10/01 | Fri 20/11/27
71 | External User Application - Common Feature- other features- Action Page (user will have common feature in the page) | 42 days | Thu 20/10/01 | Fri 20/11/27
72 | External User Application - Common Feature- other features- Track all request by Reference number (search) | 42 days | Thu 20/10/01 | Fri 20/11/27
73 | External User Application - Common Feature- other features- Table data export into CSV | 42 days | Thu 20/10/01 | Fri 20/11/27
74 | External User Application - Common Feature- other features- Upload supporting documents | 42 days | Thu 20/10/01 | Fri 20/11/27
75 | Internal User Application- User Access Management- Internal User- Registration | 42 days | Thu 20/10/01 | Fri 20/11/27
76 | Internal User Application- User Access Management- Internal User- Validate with Active Directory | 42 days | Thu 20/10/01 | Fri 20/11/27
77 | Internal User Application- User Access Management- Internal User- Request Approval | 42 days | Thu 20/10/01 | Fri 20/11/27
78 | Internal User Application- User Access Management- Internal User- Single sign on for the users | 42 days | Thu 20/10/01 | Fri 20/11/27
79 | Internal User Application- User Access Management- Internal User- Sign in | 42 days | Thu 20/10/01 | Fri 20/11/27
80 | Internal User Application- Workflow (Common Features)- Email Feature- All action will have email based on configuration | 42 days | Thu 20/10/01 | Fri 20/11/27
81 | Internal User Application- Workflow (Common Features)- SMS Feature- All action will have sms based on configuration | 42 days | Thu 20/10/01 | Fri 20/11/27
82 | Internal User Application- Workflow (Common Features)- Reports- Overridden Business Rules Report | 42 days | Thu 20/10/01 | Fri 20/11/27
83 | Internal User Application- Administrative modules- Template Management(PDF/Email/SMS)- Pro-forma Invoice | 42 days | Thu 20/10/01 | Fri 20/11/27
84 | Internal User Application- Administrative modules- User Management- Manage all the user in the hierarchy | 42 days | Thu 20/10/01 | Fri 20/11/27
85 | Internal User Application- Administrative modules- Configure Fee- Information request Categories | 42 days | Thu 20/10/01 | Fri 20/11/27
86 | Internal User Application- Administrative modules- Site Map - Site Menu based on role access | 42 days | Thu 20/10/01 | Fri 20/11/27
87 | Work Package 4- GIS- No Integration | 16 days | Fri 20/11/13 | Tue 20/12/15
88 | GIS- Spatial Viewer- Attribute Search | 17 days | Fri 20/11/13 | Tue 20/12/15
89 | GIS- Spatial Viewer- Search by Graphics | 17 days | Fri 20/11/13 | Tue 20/12/15
90 | GIS- Spatial Viewer- Search by Street Address | 17 days | Fri 20/11/13 | Tue 20/12/15
91 | GIS- Spatial Viewer- Share View Tool | 17 days | Fri 20/11/13 | Tue 20/12/15
92 | Work Package 5- UAM & IM | 25 days | Mon 20/11/02 | Tue 20/12/22
93 | External User Application - User Access Management- External User Management- Change email address | 26 days | Mon 20/11/02 | Tue 20/12/22
94 | External User Application - Common Feature- other features- Show all bookmark search for re-use | 26 days | Mon 20/11/02 | Tue 20/12/22
95 | External User Application - Issue Log- Public and registered users- Register query for registered and public user from portal | 26 days | Mon 20/11/02 | Tue 20/12/22
96 | External User Application - Issue Log- Public and registered users- Generate reference number | 26 days | Mon 20/11/02 | Tue 20/12/22
97 | External User Application - Issue Log- Public and registered users- Track reference number in the portal | 26 days | Mon 20/11/02 | Tue 20/12/22
98 | External User Application - Information Management- Single Request- Search Criteria (Free Text, Range and all other attributes INFO-A-7.10.2) | 26 days | Mon 20/11/02 | Tue 20/12/22
99 | External User Application - Information Management- Single Request- Search Data viewer/ Alpha data/ image data | 26 days | Mon 20/11/02 | Tue 20/12/22
100 | External User Application - Information Management- Single Request- Log the search transaction into database | 26 days | Mon 20/11/02 | Tue 20/12/22
101 | External User Application - Information Management- Bulk Request- Capture Request with Format, Conversion and Dissemination Medium | 26 days | Mon 20/11/02 | Tue 20/12/22
102 | External User Application - Information Management- Bulk Request- Proof of payment upload | 26 days | Mon 20/11/02 | Tue 20/12/22
103 | External User Application - Information Management- Bulk Request- Log the search transaction into database | 26 days | Mon 20/11/02 | Tue 20/12/22
104 | External User Application - Information Management- Notify manager- No Data available Notify Manager | 26 days | Mon 20/11/02 | Tue 20/12/22
105 | External User Application - Information Management- Advisory Service- Capture Advisory Services | 26 days | Mon 20/11/02 | Tue 20/12/22
106 | Internal User Application- User Access Management- Internal User- Deactivate Account as per role in hierarchy | 26 days | Mon 20/11/02 | Tue 20/12/22
107 | Internal User Application- User Access Management- Internal User- Reactivate Account | 26 days | Mon 20/11/02 | Tue 20/12/22
108 | Internal User Application- User Access Management- Internal User- User Profile | 26 days | Mon 20/11/02 | Tue 20/12/22
109 | Internal User Application- User Access Management- Reports- User summary details report | 26 days | Mon 20/11/02 | Tue 20/12/22
110 | Internal User Application- User Access Management- Reports- Detailed Users Per Quarter | 26 days | Mon 20/11/02 | Tue 20/12/22
111 | Internal User Application- User Access Management- Reports- Updated Users per Quarter | 26 days | Mon 20/11/02 | Tue 20/12/22
112 | Internal User Application- User Access Management- Reports- User Log in Statistics | 26 days | Mon 20/11/02 | Tue 20/12/22
113 | Internal User Application- Common Feature- After login- Home Page | 26 days | Mon 20/11/02 | Tue 20/12/22
114 | Internal User Application- Common Feature- After login- Notification | 26 days | Mon 20/11/02 | Tue 20/12/22
115 | Internal User Application- Common Feature- After login- Site Map | 26 days | Mon 20/11/02 | Tue 20/12/22
116 | Internal User Application- Common Feature- After login- Announcement | 26 days | Mon 20/11/02 | Tue 20/12/22
117 | Internal User Application- Common Feature- After login- Track Reference number | 26 days | Mon 20/11/02 | Tue 20/12/22
118 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Task header with details | 26 days | Mon 20/11/02 | Tue 20/12/22
119 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Task Decision section | 26 days | Mon 20/11/02 | Tue 20/12/22
120 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Audit Trail | 26 days | Mon 20/11/02 | Tue 20/12/22
121 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Annexure | 26 days | Mon 20/11/02 | Tue 20/12/22
122 | Internal User Application- Workflow (Common Features)- Holiday Calendar- Holiday Calendar | 26 days | Mon 20/11/02 | Tue 20/12/22
123 | Internal User Application- Workflow (Common Features)- Diary (Availability)- Diary | 26 days | Mon 20/11/02 | Tue 20/12/22
124 | Internal User Application- Workflow (Common Features)- ProvincialOffice Timing- Office Timing | 26 days | Mon 20/11/02 | Tue 20/12/22
125 | Work Package 6- GIS- No Integration | 8 days | Fri 20/12/18 | Wed 21/01/20
126 | GIS- Spatial Viewer- Refresh Data Sources Tool | 9 days | Fri 20/12/18 | Wed 21/01/20
127 | GIS- Spatial Viewer- Bookmark Tool | 9 days | Fri 20/12/18 | Wed 21/01/20
128 | GIS- Spatial Viewer- Print and Export Tool | 9 days | Fri 20/12/18 | Wed 21/01/20
129 | GIS- Spatial Viewer- Reset Map Tool | 9 days | Fri 20/12/18 | Wed 21/01/20
130 | Work Package 7- UAM & IM | 14 days | Tue 20/12/22 | Thu 21/01/28
131 | External User Application - User Access Management- External User Management- Request for Delegation Role | 15 days | Tue 20/12/22 | Thu 21/01/28
132 | External User Application - Fee Calculator- Public and registered users- View the fee and download quote | 15 days | Tue 20/12/22 | Thu 21/01/28
133 | External User Application - Information Management- Bulk Request- Cancel Request | 15 days | Tue 20/12/22 | Thu 21/01/28
134 | External User Application - Information Management- Template Search (Bulk Request)- Download Predefine Template | 15 days | Tue 20/12/22 | Thu 21/01/28
135 | External User Application - Information Management- Template Search (Bulk Request)- Upload and Validate Template | 15 days | Tue 20/12/22 | Thu 21/01/28
136 | External User Application - Information Management- Template Search (Bulk Request)- Search result viewer | 15 days | Tue 20/12/22 | Thu 21/01/28
137 | External User Application - Information Management- Pre-packaged Data- Subscribe | 15 days | Tue 20/12/22 | Thu 21/01/28
138 | External User Application - Information Management- Pre-packaged Data- Pre-Packaged data notification and Bulk request trigger | 15 days | Tue 20/12/22 | Thu 21/01/28
139 | Internal User Application- Single Request- Search- Search Criteria | 15 days | Tue 20/12/22 | Thu 21/01/28
140 | Internal User Application- Single Request- Search- Search Data viewer/ Alpha data/ image data | 15 days | Tue 20/12/22 | Thu 21/01/28
141 | Internal User Application- Single Request- Search- Capture Requestor Information | 15 days | Tue 20/12/22 | Thu 21/01/28
142 | Internal User Application- Single Request- Search- Information request (Internally) | 15 days | Tue 20/12/22 | Thu 21/01/28
143 | Internal User Application- Single Request- Search- Log the search transaction into database | 15 days | Tue 20/12/22 | Thu 21/01/28
144 | Internal User Application- Single Request- Notify Manager- No Data available Notify Manager | 15 days | Tue 20/12/22 | Thu 21/01/28
145 | Internal User Application- Single Request- Notify Manager- Process the missing data request by internal user | 15 days | Tue 20/12/22 | Thu 21/01/28
146 | Internal User Application- Bulk Request- Search- Capture Request with Format, Conversion and Dissemination Medium | 15 days | Tue 20/12/22 | Thu 21/01/28
147 | Internal User Application- Bulk Request- Process the request- Invoice generation | 15 days | Tue 20/12/22 | Thu 21/01/28
148 | Internal User Application- Bulk Request- Process the request- Payment Confirmation | 15 days | Tue 20/12/22 | Thu 21/01/28
149 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Property summary | 15 days | Tue 20/12/22 | Thu 21/01/28
150 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Zoom to map with boundary(map pop out full view) | 15 days | Tue 20/12/22 | Thu 21/01/28
151 | Internal User Application- Workflow (Common Features)- Task Profile- All the details of task | 15 days | Tue 20/12/22 | Thu 21/01/28
152 | Internal User Application- Workflow (Common Features)- Task Referral- Create referral request | 15 days | Tue 20/12/22 | Thu 21/01/28
153 | Internal User Application- Workflow (Common Features)- Task Referral- Submit referral | 15 days | Tue 20/12/22 | Thu 21/01/28
154 | Internal User Application- Workflow (Common Features)- Task Referral- View referral status | 15 days | Tue 20/12/22 | Thu 21/01/28
155 | Internal User Application- Workflow (Common Features)- Delegate Role- Delegation of User | 15 days | Tue 20/12/22 | Thu 21/01/28
156 | Internal User Application- Workflow (Common Features)- Delegate Role- mirror of inbox | 15 days | Tue 20/12/22 | Thu 21/01/28
157 | Internal User Application- Workflow (Common Features)- Task Management- Inbox/Task Allocation | 15 days | Tue 20/12/22 | Thu 21/01/28
158 | Internal User Application- Workflow (Common Features)- Task Management- Cancel Task | 15 days | Tue 20/12/22 | Thu 21/01/28
159 | Internal User Application- Workflow (Common Features)- Task Management- Expedite Task | 15 days | Tue 20/12/22 | Thu 21/01/28
160 | Internal User Application- Workflow (Common Features)- Task Management- Close Task | 15 days | Tue 20/12/22 | Thu 21/01/28
161 | Internal User Application- Workflow (Common Features)- Task Management- Reassign Task | 15 days | Tue 20/12/22 | Thu 21/01/28
162 | Internal User Application- Workflow (Common Features)- Task Management- Send Task to another province | 15 days | Tue 20/12/22 | Thu 21/01/28
163 | Work Package 8- IM | 20 days | Fri 21/01/29 | Thu 21/02/25
164 | Internal User Application- Single Request- Reports- Production Report | 20 days | Fri 21/01/29 | Thu 21/02/25
165 | Internal User Application- Bulk Request- Search- Template Search | 20 days | Fri 21/01/29 | Thu 21/02/25
166 | Internal User Application- Bulk Request- Search- Pre-Packaged data request | 20 days | Fri 21/01/29 | Thu 21/02/25
167 | Internal User Application- Bulk Request- Process the request- Process request by Internal user | 20 days | Fri 21/01/29 | Thu 21/02/25
168 | Internal User Application- Bulk Request- Advisory Service- Process advisory service | 20 days | Fri 21/01/29 | Thu 21/02/25
169 | Internal User Application- Bulk Request- Dispatch- Capture Dispatch details | 20 days | Fri 21/01/29 | Thu 21/02/25
170 | Internal User Application- Reports- Reports- Productivity/production report | 20 days | Fri 21/01/29 | Thu 21/02/25
171 | Internal User Application- Reports- Reports- User Report | 20 days | Fri 21/01/29 | Thu 21/02/25
172 | Internal User Application- Reports- Reports- Notification Report | 20 days | Fri 21/01/29 | Thu 21/02/25
173 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Contextual help | 20 days | Fri 21/01/29 | Thu 21/02/25
174 | Internal User Application- Tools- LPI Profile- LPI Profile | 20 days | Fri 21/01/29 | Thu 21/02/25
175 | Work Package 9- GIS- With Integration | 35 days | Fri 21/01/22 | Thu 21/03/11
176 | GIS- Spatial Viewer- Identify Tool | 35 days | Fri 21/01/22 | Thu 21/03/11
177 | GIS- Spatial Viewer- Bookmark Tool | 35 days | Fri 21/01/22 | Thu 21/03/11
178 | GIS- Spatial Viewer- Attribute Search | 35 days | Fri 21/01/22 | Thu 21/03/11
179 | GIS- Spatial Viewer- Search by Graphics | 35 days | Fri 21/01/22 | Thu 21/03/11
180 | GIS- Spatial Viewer- Search by Street Address | 35 days | Fri 21/01/22 | Thu 21/03/11
181 | GIS- Spatial Viewer- Share View Tool | 35 days | Fri 21/01/22 | Thu 21/03/11
182 | GIS- Spatial Viewer- Map System Administration-Information Management Module | 35 days | Fri 21/01/22 | Thu 21/03/11
183 | GIS- Spatial Viewer- Alpha Numeric Data Extraction Tool | 35 days | Fri 21/01/22 | Thu 21/03/11
184 | GIS- Spatial Viewer- Provision of Pre-packaged Data | 35 days | Fri 21/01/22 | Thu 21/03/11
185 | GIS- Spatial Viewer- Tracking of all information that is downloaded from the Spatial Viewer | 35 days | Fri 21/01/22 | Thu 21/03/11
186 | GIS- Spatial Viewer- User Access Management Module | 35 days | Fri 21/01/22 | Thu 21/03/11
187 | Work Package 10- Dashboards, Back End services | 20 days | Fri 21/02/26 | Fri 21/03/26
188 | Internal User Application- Tools- Data Viewer- SQL Developer (Simple Query) | 20 days | Fri 21/02/26 | Fri 21/03/26
189 | Internal User Application- Dashboards- Dashboards- National Administrator | 20 days | Fri 21/02/26 | Fri 21/03/26
190 | Internal User Application- Dashboards- Dashboards- Provincial Administrator | 20 days | Fri 21/02/26 | Fri 21/03/26
191 | Internal User Application- Dashboards- Dashboards- Information Manger | 20 days | Fri 21/02/26 | Fri 21/03/26
192 | Internal User Application- Dashboards- Dashboards- Manager | 20 days | Fri 21/02/26 | Fri 21/03/26
193 | Internal User Application- Dashboards- Dashboards- User | 20 days | Fri 21/02/26 | Fri 21/03/26
194 | Back end services- System - Pre-packaged Data- Notify or supply Pre-Packaged data | 20 days | Fri 21/02/26 | Fri 21/03/26
195 | Back end services- System - Pre-packaged Data- Notify user any data changes for subscribe data | 20 days | Fri 21/02/26 | Fri 21/03/26
196 | Work Package 11- Updated Knowledge Base | 20 days | Tue 21/03/16 | Thu 21/04/15
197 | Knowledge base- Documentation- Application- API Reference documentation | 20 days | Tue 21/03/16 | Thu 21/04/15
198 | Knowledge base- Documentation- Application- API Front End feature mapping document | 20 days | Tue 21/03/16 | Thu 21/04/15
199 | Knowledge base- Documentation- Testing- Test Cases | 20 days | Tue 21/03/16 | Thu 21/04/15
200 | Knowledge base- Documentation- Testing- Test Plan | 20 days | Tue 21/03/16 | Thu 21/04/15
201 | Knowledge base- Documentation- Testing- Test Report | 20 days | Tue 21/03/16 | Thu 21/04/15
202 | Knowledge base- Documentation- User Manual- External User Application | 20 days | Tue 21/03/16 | Thu 21/04/15
203 | Knowledge base- Documentation- User Manual- Internal User Application | 20 days | Tue 21/03/16 | Thu 21/04/15
204 | Knowledge base- Documentation- Training Material- Role based Training | 20 days | Tue 21/03/16 | Thu 21/04/15
205 | Knowledge base- Help File- Training Material- HTML based Help | 20 days | Tue 21/03/16 | Thu 21/04/15
206 | Knowledge base- Help File- Training Material- Fee text search help | 20 days | Tue 21/03/16 | Thu 21/04/15
207 | Review Session 1- Wireframes, Workflow Studio- DW Environment | 1 day | Fri 20/10/30 | Fri 20/10/30 | 36
208 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Theme\Master Layout | 1 day | Fri 20/10/30 | Fri 20/10/30
209 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Application HTML Flow | 1 day | Fri 20/10/30 | Fri 20/10/30
210 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Registration Page | 1 day | Fri 20/10/30 | Fri 20/10/30
211 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- Sign in | 1 day | Fri 20/10/30 | Fri 20/10/30
212 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- After login- Home Page | 1 day | Fri 20/10/30 | Fri 20/10/30
213 | Wireframe PDF and HTML- UX Design (wireframe PDF and HTML)- External User/ Internal User- All the modules wireframe | 1 day | Fri 20/10/30 | Fri 20/10/30
214 | Internal User Application- Workflow (Common Features)- Workflow Studio- Create new process flow - National | 1 day | Fri 20/10/30 | Fri 20/10/30
215 | Internal User Application- Workflow (Common Features)- Workflow Studio- Define all the configuration | 1 day | Fri 20/10/30 | Fri 20/10/30
216 | Internal User Application- Workflow (Common Features)- Workflow Studio- Publish process for all Provinces | 1 day | Fri 20/10/30 | Fri 20/10/30
217 | Internal User Application- Workflow (Common Features)- Workflow Studio- Province will have feature to customize the process flow | 1 day | Fri 20/10/30 | Fri 20/10/30
218 | Internal User Application- Workflow (Common Features)- Workflow Studio- Configuration Turnaround Time | 1 day | Fri 20/10/30 | Fri 20/10/30
219 | Internal User Application- Workflow (Common Features)- Workflow Studio- Configure Request prefix and Suffix | 1 day | Fri 20/10/30 | Fri 20/10/30
220 | Internal User Application- Workflow (Common Features)- Workflow Studio- Tracking number configuration for all type of request | 1 day | Fri 20/10/30 | Fri 20/10/30
221 | Internal User Application- Administrative modules- List management- List Management of system | 1 day | Fri 20/10/30 | Fri 20/10/30
222 | Review Session 2- GIS- No Integration- DW Environment | 1 day | Thu 20/11/12 | Thu 20/11/12 | 51
223 | GIS- Spatial Viewer- Measure Tool | 1 day | Thu 20/11/12 | Thu 20/11/12
224 | GIS- Spatial Viewer- Layer Manager | 1 day | Thu 20/11/12 | Thu 20/11/12
225 | GIS- Spatial Viewer- Map Legend | 1 day | Thu 20/11/12 | Thu 20/11/12
226 | GIS- Spatial Viewer- Identify Tool | 1 day | Thu 20/11/12 | Thu 20/11/12
227 | GIS- Spatial Viewer- Map Navigation Tools | 1 day | Thu 20/11/12 | Thu 20/11/12
228 | GIS- Spatial Viewer- Parametrised Viewer | 1 day | Thu 20/11/12 | Thu 20/11/12
229 | Review Session 3- UAM, Workflow Studio- DW Environment | 1 day | Mon 20/11/30 | Mon 20/11/30 | 58
230 | External User Application - User Access Management- External User Management- Registration (PLS, Architect , Assistance, Conveyancer and all other) | 1 day | Mon 20/11/30 | Mon 20/11/30
231 | External User Application - User Access Management- External User Management- Verify Professional Registration | 1 day | Mon 20/11/30 | Mon 20/11/30
232 | External User Application - User Access Management- External User Management- Sign in | 1 day | Mon 20/11/30 | Mon 20/11/30
233 | External User Application - User Access Management- External User Management- Deactivate account as per role in hierarchy | 1 day | Mon 20/11/30 | Mon 20/11/30
234 | External User Application - User Access Management- External User Management- Reactivate account | 1 day | Mon 20/11/30 | Mon 20/11/30
235 | External User Application - User Access Management- External User Management- PLS mange assistants | 1 day | Mon 20/11/30 | Mon 20/11/30
236 | External User Application - User Access Management- External User Management- Forget Password | 1 day | Mon 20/11/30 | Mon 20/11/30
237 | External User Application - User Access Management- External User Management- Reset Password | 1 day | Mon 20/11/30 | Mon 20/11/30
238 | External User Application - User Access Management- External User Management- User Profile | 1 day | Mon 20/11/30 | Mon 20/11/30
239 | External User Application - Common Feature- other features- Home Page | 1 day | Mon 20/11/30 | Mon 20/11/30
240 | External User Application - Common Feature- other features- Notification Section | 1 day | Mon 20/11/30 | Mon 20/11/30
241 | External User Application - Common Feature- other features- Inbox | 1 day | Mon 20/11/30 | Mon 20/11/30
242 | External User Application - Common Feature- other features- Action Page (user will have common feature in the page) | 1 day | Mon 20/11/30 | Mon 20/11/30
243 | External User Application - Common Feature- other features- Track all request by Reference number (search) | 1 day | Mon 20/11/30 | Mon 20/11/30
244 | External User Application - Common Feature- other features- Table data export into CSV | 1 day | Mon 20/11/30 | Mon 20/11/30
245 | External User Application - Common Feature- other features- Upload supporting documents | 1 day | Mon 20/11/30 | Mon 20/11/30
246 | Internal User Application- User Access Management- Internal User- Registration | 1 day | Mon 20/11/30 | Mon 20/11/30
247 | Internal User Application- User Access Management- Internal User- Validate with Active Directory | 1 day | Mon 20/11/30 | Mon 20/11/30
248 | Internal User Application- User Access Management- Internal User- Request Approval | 1 day | Mon 20/11/30 | Mon 20/11/30
249 | Internal User Application- User Access Management- Internal User- Single sign on for the users | 1 day | Mon 20/11/30 | Mon 20/11/30
250 | Internal User Application- User Access Management- Internal User- Sign in | 1 day | Mon 20/11/30 | Mon 20/11/30
251 | Internal User Application- Workflow (Common Features)- Email Feature- All action will have email based on configuration | 1 day | Mon 20/11/30 | Mon 20/11/30
252 | Internal User Application- Workflow (Common Features)- SMS Feature- All action will have sms based on configuration | 1 day | Mon 20/11/30 | Mon 20/11/30
253 | Internal User Application- Workflow (Common Features)- Reports- Overridden Business Rules Report | 1 day | Mon 20/11/30 | Mon 20/11/30
254 | Internal User Application- Administrative modules- Template Management(PDF/Email/SMS)- Pro-forma Invoice | 1 day | Mon 20/11/30 | Mon 20/11/30
255 | Internal User Application- Administrative modules- User Management- Manage all the user in the hierarchy | 1 day | Mon 20/11/30 | Mon 20/11/30
256 | Internal User Application- Administrative modules- Configure Fee- Information request Categories | 1 day | Mon 20/11/30 | Mon 20/11/30
257 | Internal User Application- Administrative modules- Site Map - Site Menu based on role access | 1 day | Mon 20/11/30 | Mon 20/11/30
258 | Review Session 4- GIS- No Integration- DW Environment | 0 days | Thu 20/12/17 | Thu 20/12/17 | 87
259 | GIS- Spatial Viewer- Attribute Search | 1 day | Thu 20/12/17 | Thu 20/12/17
260 | GIS- Spatial Viewer- Search by Graphics | 1 day | Thu 20/12/17 | Thu 20/12/17
261 | GIS- Spatial Viewer- Search by Street Address | 1 day | Thu 20/12/17 | Thu 20/12/17
262 | GIS- Spatial Viewer- Share View Tool | 1 day | Thu 20/12/17 | Thu 20/12/17
263 | Review Session 5- UAM & IM- DW Environment | 0 days | Wed 20/12/23 | Wed 20/12/23 | 92
264 | External User Application - User Access Management- External User Management- Change email address | 1 day | Wed 20/12/23 | Wed 20/12/23
265 | External User Application - Common Feature- other features- Show all bookmark search for re-use | 1 day | Wed 20/12/23 | Wed 20/12/23
266 | External User Application - Issue Log- Public and registered users- Register query for registered and public user from portal | 1 day | Wed 20/12/23 | Wed 20/12/23
267 | External User Application - Issue Log- Public and registered users- Generate reference number | 1 day | Wed 20/12/23 | Wed 20/12/23
268 | External User Application - Issue Log- Public and registered users- Track reference number in the portal | 1 day | Wed 20/12/23 | Wed 20/12/23
269 | External User Application - Information Management- Single Request- Search Criteria (Free Text, Range and all other attributes INFO-A-7.10.2) | 1 day | Wed 20/12/23 | Wed 20/12/23
270 | External User Application - Information Management- Single Request- Search Data viewer/ Alpha data/ image data | 1 day | Wed 20/12/23 | Wed 20/12/23
271 | External User Application - Information Management- Single Request- Log the search transaction into database | 1 day | Wed 20/12/23 | Wed 20/12/23
272 | External User Application - Information Management- Bulk Request- Capture Request with Format, Conversion and Dissemination Medium | 1 day | Wed 20/12/23 | Wed 20/12/23
273 | External User Application - Information Management- Bulk Request- Proof of payment upload | 1 day | Wed 20/12/23 | Wed 20/12/23
274 | External User Application - Information Management- Bulk Request- Log the search transaction into database | 1 day | Wed 20/12/23 | Wed 20/12/23
275 | External User Application - Information Management- Notify manager- No Data available Notify Manager | 1 day | Wed 20/12/23 | Wed 20/12/23
276 | External User Application - Information Management- Advisory Service- Capture Advisory Services | 1 day | Wed 20/12/23 | Wed 20/12/23
277 | Internal User Application- User Access Management- Internal User- Deactivate Account as per role in hierarchy | 1 day | Wed 20/12/23 | Wed 20/12/23
278 | Internal User Application- User Access Management- Internal User- Reactivate Account | 1 day | Wed 20/12/23 | Wed 20/12/23
279 | Internal User Application- User Access Management- Internal User- User Profile | 1 day | Wed 20/12/23 | Wed 20/12/23
280 | Internal User Application- User Access Management- Reports- User summary details report | 1 day | Wed 20/12/23 | Wed 20/12/23
281 | Internal User Application- User Access Management- Reports- Detailed Users Per Quarter | 1 day | Wed 20/12/23 | Wed 20/12/23
282 | Internal User Application- User Access Management- Reports- Updated Users per Quarter | 1 day | Wed 20/12/23 | Wed 20/12/23
283 | Internal User Application- User Access Management- Reports- User Log in Statistics | 1 day | Wed 20/12/23 | Wed 20/12/23
284 | Internal User Application- Common Feature- After login- Home Page | 1 day | Wed 20/12/23 | Wed 20/12/23
285 | Internal User Application- Common Feature- After login- Notification | 1 day | Wed 20/12/23 | Wed 20/12/23
286 | Internal User Application- Common Feature- After login- Site Map | 1 day | Wed 20/12/23 | Wed 20/12/23
287 | Internal User Application- Common Feature- After login- Announcement | 1 day | Wed 20/12/23 | Wed 20/12/23
288 | Internal User Application- Common Feature- After login- Track Reference number | 1 day | Wed 20/12/23 | Wed 20/12/23
289 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Task header with details | 1 day | Wed 20/12/23 | Wed 20/12/23
290 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Task Decision section | 1 day | Wed 20/12/23 | Wed 20/12/23
291 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Audit Trail | 1 day | Wed 20/12/23 | Wed 20/12/23
292 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Annexure | 1 day | Wed 20/12/23 | Wed 20/12/23
293 | Internal User Application- Workflow (Common Features)- Holiday Calendar- Holiday Calendar | 1 day | Wed 20/12/23 | Wed 20/12/23
294 | Internal User Application- Workflow (Common Features)- Diary (Availability)- Diary | 1 day | Wed 20/12/23 | Wed 20/12/23
295 | Internal User Application- Workflow (Common Features)- ProvincialOffice Timing- Office Timing | 1 day | Wed 20/12/23 | Wed 20/12/23
296 | Review Session 6- GIS- No Integration- DW Environment | 1 day | Thu 21/01/21 | Thu 21/01/21 | 125
297 | GIS- Spatial Viewer- Refresh Data Sources Tool | 1 day | Thu 21/01/21 | Thu 21/01/21
298 | GIS- Spatial Viewer- Bookmark Tool | 1 day | Thu 21/01/21 | Thu 21/01/21
299 | GIS- Spatial Viewer- Print and Export Tool | 1 day | Thu 21/01/21 | Thu 21/01/21
300 | GIS- Spatial Viewer- Reset Map Tool | 1 day | Thu 21/01/21 | Thu 21/01/21
301 | Review Session 7- UAM & IM- DW Environment | 1 day | Fri 21/01/29 | Fri 21/01/29 | 130
302 | External User Application - User Access Management- External User Management- Request for Delegation Role | 1 day | Fri 21/01/29 | Fri 21/01/29
303 | External User Application - Fee Calculator- Public and registered users- View the fee and download quote | 1 day | Fri 21/01/29 | Fri 21/01/29
304 | External User Application - Information Management- Bulk Request- Cancel Request | 1 day | Fri 21/01/29 | Fri 21/01/29
305 | External User Application - Information Management- Template Search (Bulk Request)- Download Predefine Template | 1 day | Fri 21/01/29 | Fri 21/01/29
306 | External User Application - Information Management- Template Search (Bulk Request)- Upload and Validate Template | 1 day | Fri 21/01/29 | Fri 21/01/29
307 | External User Application - Information Management- Template Search (Bulk Request)- Search result viewer | 1 day | Fri 21/01/29 | Fri 21/01/29
308 | External User Application - Information Management- Pre-packaged Data- Subscribe | 1 day | Fri 21/01/29 | Fri 21/01/29
309 | External User Application - Information Management- Pre-packaged Data- Pre-Packaged data notification and Bulk request trigger | 1 day | Fri 21/01/29 | Fri 21/01/29
310 | Internal User Application- Single Request- Search- Search Criteria | 1 day | Fri 21/01/29 | Fri 21/01/29
311 | Internal User Application- Single Request- Search- Search Data viewer/ Alpha data/ image data | 1 day | Fri 21/01/29 | Fri 21/01/29
312 | Internal User Application- Single Request- Search- Capture Requestor Information | 1 day | Fri 21/01/29 | Fri 21/01/29
313 | Internal User Application- Single Request- Search- Information request (Internally) | 1 day | Fri 21/01/29 | Fri 21/01/29
314 | Internal User Application- Single Request- Search- Log the search transaction into database | 1 day | Fri 21/01/29 | Fri 21/01/29
315 | Internal User Application- Single Request- Notify Manager- No Data available Notify Manager | 1 day | Fri 21/01/29 | Fri 21/01/29
316 | Internal User Application- Single Request- Notify Manager- Process the missing data request by internal user | 1 day | Fri 21/01/29 | Fri 21/01/29
317 | Internal User Application- Bulk Request- Search- Capture Request with Format, Conversion and Dissemination Medium | 1 day | Fri 21/01/29 | Fri 21/01/29
318 | Internal User Application- Bulk Request- Process the request- Invoice generation | 1 day | Fri 21/01/29 | Fri 21/01/29
319 | Internal User Application- Bulk Request- Process the request- Payment Confirmation | 1 day | Fri 21/01/29 | Fri 21/01/29
320 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Property summary | 1 day | Fri 21/01/29 | Fri 21/01/29
321 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Zoom to map with boundary(map pop out full view) | 1 day | Fri 21/01/29 | Fri 21/01/29
322 | Internal User Application- Workflow (Common Features)- Task Profile- All the details of task | 1 day | Fri 21/01/29 | Fri 21/01/29
323 | Internal User Application- Workflow (Common Features)- Task Referral- Create referral request | 1 day | Fri 21/01/29 | Fri 21/01/29
324 | Internal User Application- Workflow (Common Features)- Task Referral- Submit referral | 1 day | Fri 21/01/29 | Fri 21/01/29
325 | Internal User Application- Workflow (Common Features)- Task Referral- View referral status | 1 day | Fri 21/01/29 | Fri 21/01/29
326 | Internal User Application- Workflow (Common Features)- Delegate Role- Delegation of User | 1 day | Fri 21/01/29 | Fri 21/01/29
327 | Internal User Application- Workflow (Common Features)- Delegate Role- mirror of inbox | 1 day | Fri 21/01/29 | Fri 21/01/29
328 | Internal User Application- Workflow (Common Features)- Task Management- Inbox/Task Allocation | 1 day | Fri 21/01/29 | Fri 21/01/29
329 | Internal User Application- Workflow (Common Features)- Task Management- Cancel Task | 1 day | Fri 21/01/29 | Fri 21/01/29
330 | Internal User Application- Workflow (Common Features)- Task Management- Expedite Task | 1 day | Fri 21/01/29 | Fri 21/01/29
331 | Internal User Application- Workflow (Common Features)- Task Management- Close Task | 1 day | Fri 21/01/29 | Fri 21/01/29
332 | Internal User Application- Workflow (Common Features)- Task Management- Reassign Task | 1 day | Fri 21/01/29 | Fri 21/01/29
333 | Internal User Application- Workflow (Common Features)- Task Management- Send Task to another province | 1 day | Fri 21/01/29 | Fri 21/01/29
334 | Review Session 8- IM- DW Environment | 1 day | Fri 21/02/26 | Fri 21/02/26 | 163
335 | Internal User Application- Single Request- Reports- Production Report | 1 day | Fri 21/02/26 | Fri 21/02/26
336 | Internal User Application- Bulk Request- Search- Template Search | 1 day | Fri 21/02/26 | Fri 21/02/26
337 | Internal User Application- Bulk Request- Search- Pre-Packaged data request | 1 day | Fri 21/02/26 | Fri 21/02/26
338 | Internal User Application- Bulk Request- Process the request- Process request by Internal user | 1 day | Fri 21/02/26 | Fri 21/02/26
339 | Internal User Application- Bulk Request- Advisory Service- Process advisory service | 1 day | Fri 21/02/26 | Fri 21/02/26
340 | Internal User Application- Bulk Request- Dispatch- Capture Dispatch details | 1 day | Fri 21/02/26 | Fri 21/02/26
341 | Internal User Application- Reports- Reports- Productivity/production report | 1 day | Fri 21/02/26 | Fri 21/02/26
342 | Internal User Application- Reports- Reports- User Report | 1 day | Fri 21/02/26 | Fri 21/02/26
343 | Internal User Application- Reports- Reports- Notification Report | 1 day | Fri 21/02/26 | Fri 21/02/26
344 | Internal User Application- Workflow (Common Features)- Task Page (Action Page)- Contextual help | 1 day | Fri 21/02/26 | Fri 21/02/26
345 | Internal User Application- Tools- LPI Profile- LPI Profile | 1 day | Fri 21/02/26 | Fri 21/02/26
346 | Review Session 9- GIS- With Integration- DW Environment | 1 day | Thu 21/03/11 | Thu 21/03/11 | 175
347 | GIS- Spatial Viewer- Identify Tool | 1 day | Thu 21/03/11 | Thu 21/03/11
348 | GIS- Spatial Viewer- Bookmark Tool | 1 day | Thu 21/03/11 | Thu 21/03/11
349 | GIS- Spatial Viewer- Attribute Search | 1 day | Thu 21/03/11 | Thu 21/03/11
350 | GIS- Spatial Viewer- Search by Graphics | 1 day | Thu 21/03/11 | Thu 21/03/11
351 | GIS- Spatial Viewer- Search by Street Address | 1 day | Thu 21/03/11 | Thu 21/03/11
352 | GIS- Spatial Viewer- Share View Tool | 1 day | Thu 21/03/11 | Thu 21/03/11
353 | GIS- Spatial Viewer- Map System Administration-Information Management Module | 1 day | Thu 21/03/11 | Thu 21/03/11
354 | GIS- Spatial Viewer- Alpha Numeric Data Extraction Tool | 1 day | Thu 21/03/11 | Thu 21/03/11
355 | GIS- Spatial Viewer- Provision of Pre-packaged Data | 1 day | Thu 21/03/11 | Thu 21/03/11
356 | GIS- Spatial Viewer- Tracking of all information that is downloaded from the Spatial Viewer | 1 day | Thu 21/03/11 | Thu 21/03/11
357 | GIS- Spatial Viewer- User Access Management Module | 1 day | Thu 21/03/11 | Thu 21/03/11
358 | Review Session 10- Dashboards, Back End services- DW Environment | 1 day | Mon 21/03/29 | Mon 21/03/29 | 187
359 | Internal User Application- Tools- Data Viewer- SQL Developer (Simple Query) | 1 day | Mon 21/03/29 | Mon 21/03/29
360 | Internal User Application- Dashboards- Dashboards- National Administrator | 1 day | Mon 21/03/29 | Mon 21/03/29
361 | Internal User Application- Dashboards- Dashboards- Provincial Administrator | 1 day | Mon 21/03/29 | Mon 21/03/29
362 | Internal User Application- Dashboards- Dashboards- Information Manger | 1 day | Mon 21/03/29 | Mon 21/03/29
363 | Internal User Application- Dashboards- Dashboards- Manager | 1 day | Mon 21/03/29 | Mon 21/03/29
364 | Internal User Application- Dashboards- Dashboards- User | 1 day | Mon 21/03/29 | Mon 21/03/29
365 | Back end services- System - Pre-packaged Data- Notify or supply Pre-Packaged data | 1 day | Mon 21/03/29 | Mon 21/03/29
366 | Back end services- System - Pre-packaged Data- Notify user any data changes for subscribe data | 1 day | Mon 21/03/29 | Mon 21/03/29
367 | Review Session 11- Updated Knowledge Base- DW Environment | 1 day | Thu 21/04/15 | Thu 21/04/15 | 196
368 | Knowledge base- Documentation- Application- API Reference documentation | 1 day | Thu 21/04/15 | Thu 21/04/15
369 | Knowledge base- Documentation- Application- API Front End feature mapping document | 1 day | Thu 21/04/15 | Thu 21/04/15
370 | Knowledge base- Documentation- Testing- Test Cases | 1 day | Thu 21/04/15 | Thu 21/04/15
371 | Knowledge base- Documentation- Testing- Test Plan | 1 day | Thu 21/04/15 | Thu 21/04/15
372 | Knowledge base- Documentation- Testing- Test Report | 1 day | Thu 21/04/15 | Thu 21/04/15
373 | Knowledge base- Documentation- User Manual- External User Application | 1 day | Thu 21/04/15 | Thu 21/04/15
374 | Knowledge base- Documentation- User Manual- Internal User Application | 1 day | Thu 21/04/15 | Thu 21/04/15
375 | Knowledge base- Documentation- Training Material- Role based Training | 1 day | Thu 21/04/15 | Thu 21/04/15
376 | Knowledge base- Help File- Training Material- HTML based Help | 1 day | Thu 21/04/15 | Thu 21/04/15
377 | Knowledge base- Help File- Training Material- Fee text search help | 1 day | Thu 21/04/15 | Thu 21/04/15
378 | Revision of test cases | 2 days | Thu 21/04/29 | Fri 21/04/30 | 30
379 | Testing- Data World | 5 days | Mon 21/05/03 | Fri 21/05/07 | 378
380 | Test report- Data World | 4 days | Mon 21/05/10 | Thu 21/05/13 | 379
381 | Submission of test report to client | 1 day | Fri 21/05/14 | Fri 21/05/14 | 380
382 | Client review of test report | 2 days | Mon 21/05/17 | Tue 21/05/18 | 381
383 | Demonstration to client- DW environment | 1 day | Wed 21/05/19 | Wed 21/05/19 | 382
384 | Further client feedback incorporated | 5 days | Thu 21/05/20 | Wed 21/05/26 | 383
385 | Update of existing user manuals/ helpfiles / material | 4 days | Thu 21/05/27 | Tue 21/06/01 | 384
386 | Rollout to Client Test environment | 2 days | Wed 21/06/02 | Thu 21/06/03 | 385
387 | DW- client environment testing | 2 days | Fri 21/06/04 | Mon 21/06/07 | 386
388 | Test report creation | 2 days | Tue 21/06/08 | Wed 21/06/09 | 387
389 | Submission of test report to client | 1 day | Thu 21/06/10 | Thu 21/06/10 | 388
390 | Client review of test report | 3 days | Fri 21/06/11 | Tue 21/06/15 | 389
391 | UAT- End to End, including changes to previous system functionality as per addendums | 3 days | Thu 21/06/17 | Mon 21/06/21 | 390
392 | Creation of revised delivery pack | 3 days | Tue 21/06/22 | Thu 21/06/24 | 391
393 | Review & Signoff - revised delivery pack | 3 days | Fri 21/06/25 | Tue 21/06/29 | 392
394 | Production Rollout- Release 1 | 3 days | Wed 21/06/30 | Fri 21/07/02 | 393
395 | PSC Approval- Go Ahead to proceed with Release 2 | 1 day | Mon 21/07/05 | Mon 21/07/05 | 394
396 | Release 2 - Release of Purchase Order | 651 days | Wed 19/11/13 | Mon 22/09/05
397 | BRS Phase | 18 days | Wed 19/11/13 | Fri 19/12/06
398 | BRS Signoff - module 4 (Reservations) | 1 day | Wed 19/11/13 | Wed 19/11/13
399 | BRS signoff- module 5 (Lodgement) | 1 day | Wed 19/11/13 | Wed 19/11/13
400 | BRS signoff- module 6 (Examinations) | 5 days | Mon 19/12/02 | Fri 19/12/06
401 | FRS phase | 60 days | Tue 21/07/06 | Wed 21/09/29 | 395
402 | Preparation for FRS Sessions | 5 days | Tue 21/07/06 | Mon 21/07/12
403 | Sessions with Deeds PTA/ SG PTA | 4 days | Tue 21/07/13 | Fri 21/07/16 | 402
404 | FRS Sessions | 5 days | Mon 21/07/19 | Fri 21/07/23 | 403
405 | Module 5 (Lodgement) | 26 days | Mon 21/07/26 | Tue 21/08/31
406 | FRS Documented, submitted for Project team review | 11 days | Mon 21/07/26 | Tue 21/08/10 | 404
407 | Project team review | 2 days | Wed 21/08/11 | Thu 21/08/12 | 406
408 | Updated based on feedback from project team, Traceability Matrix created | 4 days | Fri 21/08/13 | Wed 21/08/18 | 407
409 | SG Review | 3 days | Thu 21/08/19 | Mon 21/08/23 | 408
410 | SG Feedback incorporated | 3 days | Tue 21/08/24 | Thu 21/08/26 | 409
411 | Final review and signoff | 3 days | Fri 21/08/27 | Tue 21/08/31 | 410
412 | Module 6 (Examinations) | 24 days | Wed 21/08/11 | Mon 21/09/13
413 | FRS Documented, submitted for Project team review | 10 days | Wed 21/08/11 | Tue 21/08/24 | 406
414 | Project team review | 2 days | Wed 21/08/25 | Thu 21/08/26 | 413
415 | Updated based on feedback from project team, Traceability Matrix created | 3 days | Fri 21/08/27 | Tue 21/08/31 | 414
416 | SG Review | 3 days | Wed 21/09/01 | Fri 21/09/03 | 415
417 | SG Feedback incorporated | 3 days | Mon 21/09/06 | Wed 21/09/08 | 416
418 | Final review and signoff | 3 days | Thu 21/09/09 | Mon 21/09/13 | 417
419 | Module 4 (Reservations) | 25 days | Wed 21/08/25 | Wed 21/09/29
420 | FRS Documented, submitted for Project team review | 10 days | Wed 21/08/25 | Tue 21/09/07 | 413
421 | Project team review | 2 days | Wed 21/09/08 | Thu 21/09/09 | 420
422 | Updated based on feedback from project team, Traceability Matrix created | 4 days | Fri 21/09/10 | Wed 21/09/15 | 421
423 | SG Review | 3 days | Thu 21/09/16 | Mon 21/09/20 | 422
424 | SG Feedback incorporated | 3 days | Tue 21/09/21 | Thu 21/09/23 | 423
425 | Final review and signoff | 3 days | Mon 21/09/27 | Wed 21/09/29 | 424
426 | Development Phase, Testing Phase | 231 days | Wed 21/09/01 | Mon 22/09/05
427 | Module 5 (Lodgement) | 98 days | Wed 21/09/01 | Mon 22/02/21
428 | Development & Unit Testing | 70 days | Wed 21/09/01 | Wed 22/01/12 | 411
429 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 10 days | Thu 22/01/13 | Wed 22/01/26 | 428
430 | Deploy to client environment, DW to test | 2 days | Thu 22/01/27 | Fri 22/01/28 | 429
431 | Training | 2 days | Mon 22/01/31 | Tue 22/02/01 | 430
432 | Client Testing - HO testing | 2 days | Wed 22/02/02 | Thu 22/02/03 | 431
433 | Resolution, Redeployment, Confirmation of issues raised by HO | 8 days | Fri 22/02/04 | Tue 22/02/15 | 432
434 | Training | 2 days | Wed 22/02/16 | Thu 22/02/17 | 433
435 | Signoff/ Acceptance of testing by SG Offices | 2 days | Fri 22/02/18 | Mon 22/02/21 | 434
436 | Module 6 (Examinations) | 73 days | Tue 22/02/22 | Thu 22/06/09
437 | Development & Unit Testing | 45 days | Tue 22/02/22 | Fri 22/04/29 | 435
438 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 10 days | Tue 22/05/03 | Mon 22/05/16 | 437
439 | Deploy to client environment, DW to test | 2 days | Tue 22/05/17 | Wed 22/05/18 | 438
440 | Training | 2 days | Thu 22/05/19 | Fri 22/05/20 | 439
441 | Client Testing - HO testing | 2 days | Mon 22/05/23 | Tue 22/05/24 | 440
442 | Resolution, Redeployment, Confirmation of issues raised by HO | 8 days | Wed 22/05/25 | Fri 22/06/03 | 441
443 | Training | 2 days | Mon 22/06/06 | Tue 22/06/07 | 442
444 | Signoff/ Acceptance of testing by SG Offices | 2 days | Wed 22/06/08 | Thu 22/06/09 | 443
445 | Module 4 (Reservations) | 49 days | Fri 22/06/10 | Fri 22/08/19
446 | Development & Unit Testing | 24 days | Fri 22/06/10 | Thu 22/07/14 | 444
447 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 10 days | Fri 22/07/15 | Thu 22/07/28 | 446
448 | Deploy to client environment, DW to test | 2 days | Fri 22/07/29 | Mon 22/08/01 | 447
449 | Training | 1 day | Tue 22/08/02 | Tue 22/08/02 | 448
450 | Client Testing - HO testing | 1 day | Wed 22/08/03 | Wed 22/08/03 | 449
451 | Resolution, Redeployment, Confirmation of issues raised by HO | 8 days | Thu 22/08/04 | Tue 22/08/16 | 450
452 | Training | 1 day | Wed 22/08/17 | Wed 22/08/17 | 451
453 | Signoff/ Acceptance of testing by SG Offices | 2 days | Thu 22/08/18 | Fri 22/08/19 | 452
454 | Release 2 Signoff | 5 days | Mon 22/08/22 | Fri 22/08/26 | 453
455 | Production Rollout- Release 2 | 5 days | Mon 22/08/29 | Fri 22/09/02 | 454
456 | PSC Approval- Go Ahead to proceed with Release 3 | 1 day | Mon 22/09/05 | Mon 22/09/05 | 455
457 | Release 3- Release of Purchase Order | 292 days | Tue 22/09/06 | Tue 23/11/21
458 | BRS Phase | 47 days | Tue 22/09/06 | Wed 22/11/09
459 | Module 7 (Archive) | 23 days | Tue 22/09/06 | Thu 22/10/06
460 | BRS Documented, submitted for Project team review | 8 days | Tue 22/09/06 | Thu 22/09/15 | 456
461 | Project team review | 2 days | Fri 22/09/16 | Mon 22/09/19 | 460
462 | Updated based on feedback from project team | 2 days | Tue 22/09/20 | Wed 22/09/21 | 461
463 | SG Review | 5 days | Thu 22/09/22 | Wed 22/09/28 | 462
464 | SG Feedback incorporated | 3 days | Thu 22/09/29 | Mon 22/10/03 | 463
465 | Final review and signoff | 3 days | Tue 22/10/04 | Thu 22/10/06 | 464
466 | Module 8 (Maintenance) | 23 days | Fri 22/09/16 | Tue 22/10/18
467 | BRS Documented, submitted for Project team review | 8 days | Fri 22/09/16 | Tue 22/09/27 | 460
468 | Project team review | 2 days | Wed 22/09/28 | Thu 22/09/29 | 467
469 | Updated based on feedback from project team | 2 days | Fri 22/09/30 | Mon 22/10/03 | 468
470 | SG Review | 5 days | Tue 22/10/04 | Mon 22/10/10 | 469
471 | SG Feedback incorporated | 3 days | Tue 22/10/11 | Thu 22/10/13 | 470
472 | Final review and signoff | 3 days | Fri 22/10/14 | Tue 22/10/18 | 471
473 | Module 9 (Reports) | 23 days | Wed 22/09/28 | Fri 22/10/28
474 | Review and revision of Reports per module | 8 days | Wed 22/09/28 | Fri 22/10/07 | 467
475 | Project team review | 2 days | Mon 22/10/10 | Tue 22/10/11 | 474
476 | Updated based on feedback from project team | 2 days | Wed 22/10/12 | Thu 22/10/13 | 475
477 | SG Review | 5 days | Fri 22/10/14 | Thu 22/10/20 | 476
478 | SG Feedback incorporated | 3 days | Fri 22/10/21 | Tue 22/10/25 | 477
479 | Final review and signoff | 3 days | Wed 22/10/26 | Fri 22/10/28 | 478
480 | Module 10 (Common Tools) | 23 days | Mon 22/10/10 | Wed 22/11/09
481 | Review and revision of common tools per module | 8 days | Mon 22/10/10 | Wed 22/10/19 | 474
482 | Project team review | 2 days | Thu 22/10/20 | Fri 22/10/21 | 481
483 | Updated based on feedback from project team | 2 days | Mon 22/10/24 | Tue 22/10/25 | 482
484 | SG Review | 5 days | Wed 22/10/26 | Tue 22/11/01 | 483
485 | SG Feedback incorporated | 3 days | Wed 22/11/02 | Fri 22/11/04 | 484
486 | Final review and signoff | 3 days | Mon 22/11/07 | Wed 22/11/09 | 485
487 | FRS Phase | 52 days | Thu 22/11/10 | Tue 23/02/14
488 | Preparation for FRS Sessions | 2 days | Thu 22/11/10 | Fri 22/11/11 | 486
489 | FRS Sessions | 7 days | Mon 22/11/14 | Tue 22/11/22 | 488
490 | Module 7 (Archive) | 23 days | Wed 22/11/23 | Tue 23/01/17
491 | FRS Documented, submitted for Project team review | 10 days | Wed 22/11/23 | Tue 22/12/06 | 489
492 | Project team review | 2 days | Wed 22/12/07 | Thu 22/12/08 | 491
493 | Updated based on feedback from project team, Traceability Matrix created | 2 days | Fri 22/12/09 | Mon 22/12/12 | 492
494 | SG Review | 3 days | Tue 22/12/13 | Mon 23/01/09 | 493
495 | SG Feedback incorporated | 3 days | Tue 23/01/10 | Thu 23/01/12 | 494
496 | Final review and signoff | 3 days | Fri 23/01/13 | Tue 23/01/17 | 495
497 | Module 8 (Maintenance) | 23 days | Wed 22/12/07 | Tue 23/01/31
498 | FRS Documented, submitted for Project team review | 10 days | Wed 22/12/07 | Thu 23/01/12 | 491
499 | Project team review | 2 days | Fri 23/01/13 | Mon 23/01/16 | 498
500 | Updated based on feedback from project team, Traceability Matrix created | 2 days | Tue 23/01/17 | Wed 23/01/18 | 499
501 | SG Review | 3 days | Thu 23/01/19 | Mon 23/01/23 | 500
502 | SG Feedback incorporated | 3 days | Tue 23/01/24 | Thu 23/01/26 | 501
503 | Final review and signoff | 3 days | Fri 23/01/27 | Tue 23/01/31 | 502
504 | Module 9 (Reports) | 18 days | Fri 23/01/13 | Tue 23/02/07
505 | FRS per previous module reviewed, report section submitted for Project team review | 5 days | Fri 23/01/13 | Thu 23/01/19 | 498
506 | Project team review | 2 days | Fri 23/01/20 | Mon 23/01/23 | 505
507 | Updated based on feedback from project team, Traceability Matrix created | 2 days | Tue 23/01/24 | Wed 23/01/25 | 506
508 | SG Review | 3 days | Thu 23/01/26 | Mon 23/01/30 | 507
509 | SG Feedback incorporated | 3 days | Tue 23/01/31 | Thu 23/02/02 | 508
510 | Final review and signoff | 3 days | Fri 23/02/03 | Tue 23/02/07 | 509
511 | Module 10 (Common Tools) | 18 days | Fri 23/01/20 | Tue 23/02/14
512 | FRS per previous module reviewed, submitted for Project team review | 5 days | Fri 23/01/20 | Thu 23/01/26 | 505
513 | Project team review | 2 days | Fri 23/01/27 | Mon 23/01/30 | 512
514 | Updated based on feedback from project team, Traceability Matrix created | 2 days | Tue 23/01/31 | Wed 23/02/01 | 513
515 | SG Review | 3 days | Thu 23/02/02 | Mon 23/02/06 | 514
516 | SG Feedback incorporated | 3 days | Tue 23/02/07 | Thu 23/02/09 | 515
517 | Final review and signoff | 3 days | Fri 23/02/10 | Tue 23/02/14 | 516
518 | Development Phase, Testing Phase | 213 days | Wed 23/01/18 | Tue 23/11/21
519 | Module 7 (Archive) | 53 days | Wed 23/01/18 | Mon 23/04/03
520 | Development & Unit Testing | 27 days | Wed 23/01/18 | Thu 23/02/23 | 496
521 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 10 days | Fri 23/02/24 | Thu 23/03/09 | 520
522 | Deploy to client environment, DW to test | 2 days | Fri 23/03/10 | Mon 23/03/13 | 521
523 | Training | 1 day | Tue 23/03/14 | Tue 23/03/14 | 522
524 | Client Testing - HO testing | 2 days | Wed 23/03/15 | Thu 23/03/16 | 523
525 | Resolution, Redeployment, Confirmation of issues raised by HO | 8 days | Fri 23/03/17 | Wed 23/03/29 | 524
526 | Training | 1 day | Thu 23/03/30 | Thu 23/03/30 | 525
527 | Signoff/ Acceptance of testing by SG Offices | 2 days | Fri 23/03/31 | Mon 23/04/03 | 526
528 | Module 8 (Maintenance) | 90 days | Tue 23/04/04 | Tue 23/08/15
529 | Development & Unit Testing | 65 days | Tue 23/04/04 | Mon 23/07/10 | 527
530 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 10 days | Tue 23/07/11 | Mon 23/07/24 | 529
531 | Deploy to client environment, DW to test | 2 days | Tue 23/07/25 | Wed 23/07/26 | 530
532 | Training | 1 day | Thu 23/07/27 | Thu 23/07/27 | 531
533 | Client Testing - HO testing | 2 days | Fri 23/07/28 | Mon 23/07/31 | 532
534 | Resolution, Redeployment, Confirmation of issues raised by HO | 7 days | Tue 23/08/01 | Thu 23/08/10 | 533
535 | Training | 1 day | Fri 23/08/11 | Fri 23/08/11 | 534
536 | Signoff/ Acceptance of testing by SG Offices | 2 days | Mon 23/08/14 | Tue 23/08/15 | 535
537 | Module 9 (Reports) | 32 days | Wed 23/08/16 | Thu 23/09/28
538 | Review Previous Development & Unit Testing | 10 days | Wed 23/08/16 | Tue 23/08/29 | 536
539 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 10 days | Wed 23/08/30 | Tue 23/09/12 | 538
540 | Deploy to client environment, DW to test | 2 days | Wed 23/09/13 | Thu 23/09/14 | 539
541 | Training | 1 day | Fri 23/09/15 | Fri 23/09/15 | 540
542 | Client Testing - HO testing | 2 days | Mon 23/09/18 | Tue 23/09/19 | 541
543 | Resolution, Redeployment, Confirmation of issues raised by HO | 4 days | Wed 23/09/20 | Mon 23/09/25 | 542
544 | Training | 1 day | Tue 23/09/26 | Tue 23/09/26 | 543
545 | Signoff/ Acceptance of testing by SG Offices | 2 days | Wed 23/09/27 | Thu 23/09/28 | 544
546 | Module 10 (Common Tools) | 28 days | Fri 23/09/29 | Tue 23/11/07
547 | Review Development & Unit Testing | 10 days | Fri 23/09/29 | Thu 23/10/12 | 545
548 | Deployed in Internal Test Environment, Tested, Feedback Incorporated, Retested, Traceability Matrix updated | 5 days | Fri 23/10/13 | Thu 23/10/19 | 547
549 | Deploy to client environment, DW to test | 2 days | Fri 23/10/20 | Mon 23/10/23 | 548
550 | Training | 1 day | Tue 23/10/24 | Tue 23/10/24 | 549
551 | Client Testing - HO testing | 2 days | Wed 23/10/25 | Thu 23/10/26 | 550
552 | Resolution, Redeployment, Confirmation of issues raised by HO | 5 days | Fri 23/10/27 | Thu 23/11/02 | 551
553 | Training | 1 day | Fri 23/11/03 | Fri 23/11/03 | 552
554 | Signoff/ Acceptance of testing by SG Offices | 2 days | Mon 23/11/06 | Tue 23/11/07 | 553
555 | Release 3 Signoff | 5 days | Wed 23/11/08 | Tue 23/11/14 | 554
556 | Production Rollout- Release 3 | 5 days | Wed 23/11/15 | Tue 23/11/21 | 555
557 | Project Closure | 44 days | Wed 23/11/22 | Mon 24/02/12 | 556
558 | Post Go-Live Support | 240 days | Tue 24/02/13 | Thu 25/01/23 | 557

## Sheet1
Coordinate System | DATUM | Comment
LO15 |  | didn't get data
LO17 | D_WGS_1984
LO19 | D_WGS_1984
LO21 | D_WGS_1984
LO23 | D_WGS_1984
LO25 | GCS_Hartebeesthoek94
LO27 | GCS_Hartebeesthoek94
LO29 | D_WGS_1984
LO31 | D_WGS_1984
LO33 | D_WGS_1984