## Sheet1
Map Tool | Review Date | Description | FRS Section
Measure Tool | 2020-11-12 | Without Integration | 6.1
Layer Manager | 2020-11-12 | Without Integration | 6.7
Map Legend | 2020-11-12 | Without Integration | 6.11
Identify Tool | 2020-11-12 | Without Integration | 6.3
Map Navigation Tools | 2020-11-12 | Without Integration | 6.2
Parametrised Viewer | 2020-11-12 | Without Integration | 8.3
Attribute Search | 2020-12-17 | Without Integration | 6.1.1
Search by Graphics | 2020-12-17 | Without Integration | 6.1.6
Search by Street Address | 2020-12-17 | Without Integration | 6.1.11
Share View Tool | 2020-12-17 | Without Integration | 6.4
Refresh Data Sources Tool | 2021-01-21 | Without Integration | 6.8
Bookmark Tool | 2021-01-21 | Without Integration | 6.6
Print and Export Tool | 2021-01-21 | Without Integration | 6.5
Reset Map Tool | 2021-01-21 | Without Integration | 6.9
Identify Tool | 2021-03-11 | With Integration | 6.3
Bookmark Tool | 2021-03-11 | With Integration | 6.8
Attribute Search | 2021-03-11 | With Integration | 6.1.1
Search by Graphics | 2021-03-11 | With Integration | 6.1.6
Search by Street Address | 2021-03-11 | With Integration | 6.1.11
Share View Tool | 2021-03-11 | With Integration | 6.4
Map System Administration will be done on the Information Management Module | 2021-03-11 | With Integration
Alpha Numeric Data Extraction Tool | 2021-03-11 | With Integration | 5.1.1.m
Provision of Pre-packaged Data | 2021-03-11 | With Integration | 5.1.1.s
track of all information that is downloaded from the Spatial Viewer | 2021-03-11 | With Integration | 5.1.1.t
User Access Management Module. | 2021-03-11 | With Integration | 5.1.1.n

## Sheet2
1st Month | 2nd Month | 3rd Month | 4th Month
Measure Tool | Attribute Search | Refresh Data Sources Tool | Identify Tool
Layer Manager | Search by Graphics | Bookmark Tool | Bookmark Tool
Map Legend | Search by Street Address | Print and Export Tool | Attribute Search
Identify Tool | Share View Tool | Reset Map Tool | Search by Graphics
Map Navigation Tools |  |  | Search by Street Address
Parametrised Viewer |  |  | Share View Tool
Map System Administration will be done on the Information Management Module
Alpha Numeric Data Extraction Tool
Provision of Pre-packaged Data
track of all information that is downloaded from the Spatial Viewer
User Access Management Module.

## Sheet3
51 | Work Package 2- GIS- No Integration | 2020-10-01 | 2020-11-11 | 82% | On Track | Developer Comment
52 | GIS- Spatial Viewer- Measure Tool | 2020-10-01 | 2020-11-16 | 100% | On Track
53 | GIS- Spatial Viewer- Layer Manager | 2020-10-01 | 2020-11-16 | 100% | On Track
54 | GIS- Spatial Viewer- Map Legend | 2020-10-01 | 2020-11-16 | 100% | On Track
55 | GIS- Spatial Viewer- Identify Tool | 2020-10-01 | 2020-11-16 | 80% | On Track | 20% is integration. Added Layer dropdown and remove Select 1,2,3… Sync with Layer Manager (Whatever Layer is on only that layer can see in Info) (as per usability request from client)
56 | GIS- Spatial Viewer- Map Navigation Tools | 2020-10-01 | 2020-11-16 | 90% | On Track | Zoom to coordinate (using LO Projection) will be available with Print functionality. Because I will add projection plugin with print module Background needs to be make visible(as per usability request from client)
57 | GIS- Spatial Viewer- Parametrised Viewer | 2020-10-01 | 2020-11-16 | 100% | On Track

## Work Package 4
Task Name | Duration | Start | Finish | Percentage Complete | Developer Comment
Work Package 4- GIS- No Integration | 16 days | Fri 20/11/13 | Tue 20/12/15 | 92% | 8% integration
GIS- Spatial Viewer- Attribute Search | 17 days | Fri 20/11/13 | Tue 20/12/15 | 90% | 10% integration
GIS- Spatial Viewer- Search by Graphics | 17 days | Fri 20/11/13 | Tue 20/12/15 | 90% | 10% integration
GIS- Spatial Viewer- Search by Street Address | 17 days | Fri 20/11/13 | Tue 20/12/15 | 100%
GIS- Spatial Viewer- Share View Tool | 17 days | Fri 20/11/13 | Tue 20/12/15 | 90% | 10% integration

## Work Package 6
Task Name | Duration | Start | Finish | Percentage Complete | Developer Comment
Work Package 6- GIS- No Integration | 9 days | Fri 20/12/18 | Wed 21/01/20 | 85%
GIS- Spatial Viewer- Refresh Data Sources Tool | 9 days | Fri 20/12/18 | Wed 21/01/20 | 80% | 20% integration
GIS- Spatial Viewer- Bookmark Tool | 9 days | Fri 20/12/18 | Wed 21/01/20 | 80% | 20% integration
GIS- Spatial Viewer- Print and Export Tool | 9 days | Fri 20/12/18 | Wed 21/01/20 | 80% | Need to impliment Feedback
GIS- Spatial Viewer- Reset Map Tool | 9 days | Fri 20/12/18 | Wed 21/01/20 | 100%

## Sheet4
Task Name | Finish(Developer Target) | Percentage Complete | Developer Comment
GIS- Spatial Viewer- Identify Tool | Thu 21/03/4 | 100%
GIS- Spatial Viewer- Bookmark Tool | Thu 21/03/4 | 100%
GIS- Spatial Viewer- Attribute Search | Thu 21/03/4 | 100%
GIS- Spatial Viewer- Search by Graphics | Thu 21/03/4 | 50%
GIS- Spatial Viewer- Search by Street Address | Thu 21/03/4 | 50%
GIS- Spatial Viewer- Share View Tool | Thu 21/03/4 | 50%
GIS- Spatial Viewer- Map System Administration-Information Management Module | Thu 21/03/4 | 100%
GIS- Spatial Viewer- Alpha Numeric Data Extraction Tool | Thu 21/03/4 | 50%
GIS- Spatial Viewer- Provision of Pre-packaged Data | Thu 21/03/4 | 50%
GIS- Spatial Viewer- Tracking of all information that is downloaded from the Spatial Viewer | Thu 21/03/4 | 50%
GIS- Spatial Viewer- User Access Management Module | Thu 21/03/4 | 50%

## Sheet5
Task Name | Service Description
GIS- Spatial Viewer- Identify Tool | will fetch the other information from database
GIS- Spatial Viewer- Bookmark Tool | in Query string pass user id and mapviewer will call WEB api to get the User Data
GIS- Spatial Viewer- Attribute Search | will fetch the other information from database
GIS- Spatial Viewer- Search by Graphics | a- Need service to pass the search criteria for tracking the downloaded GIS data b- For Bulk request need service to pass the search criteria so system can genrate the GIS data later
GIS- Spatial Viewer- Search by Street Address | eed service to pass the search criteria for tracking
GIS- Spatial Viewer- Share View Tool | need service so GIS Viewer can send the mail
GIS- Spatial Viewer- Map System Administration-Information Management Module | Will provide link, Only admin can access the link
GIS- Spatial Viewer- Alpha Numeric Data Extraction Tool | We need to discuss
GIS- Spatial Viewer- Provision of Pre-packaged Data | Writing the Window service to create the GIS data. We can put this Window service on schedular.
GIS- Spatial Viewer- Tracking of all information that is downloaded from the Spatial Viewer | Need service to pass the search criteria for tracking the downloaded GIS data
GIS- Spatial Viewer- User Access Management Module | in Query string pass user id and mapviewer will call WEB api to get the User Data